## Leverhulme
Leverhulme ECR Fellowship - Deadline 22nd February 2024 | Timeline
CoSE Launch of call | 11th October
Briefing session on Leverhulme ECR scheme | 26th October
Candidate and supporting academic to complete template | 11th October-6th November
Template submitted to scieng-submit@glasgow.ac.uk | 6th November
Templates split into Schools and passed to DoR for consideration and selection | 6th November
DoR confirms candidates from their school, including support of LKAS application | 29th November
Successful candidates notified of outcomes by Research Support office and instructed on how to submit, and who PC and RDM contacts are | 30th November
Initial costs to Project Coordinator | 6th December
LKAS application submitted | 24th January
Draft application to be submitted to your Research Development Manager | 25th January
Draft answers to HoS questions submitted to Research Development Manager/HoRD in Engineering | 30th January
Finalise costs with PC and costing submitted to workflow | 6th February
Answers to HoS questions to be sent to HoS for approval/uploading | 8th February
Submit application for institutional approval minimum 48h before funder deadline. | 20th February
https://www.leverhulme.ac.uk/early-career-fellowships
Note: include step to collate HoS Q&A and finances in Feb

## RC1851
k | Royal Commission 1851 Fellowship - Deadline 8th January 2024 | Timeline
| Template submitted to scieng-submit@glasgow.ac.uk | 10th November
| DoR confirms candidates from their school, including support of LKAS application | 16th November
| Successful candidates notified of outcomes by Research Support office and instructed on how to submit, and who PC and RDM contacts are | by 22nd November
| Initial costs to Project Coordinator | by 29th November
| LKAS application submitted | 1st December
| Draft application to be submitted to your Research Development Manager | 6th December
| Identify and confirm 2 referees | 6th December
| Draft HoS Letter of Support submitted to RDM | 11th December
| Finalise application and HoS letter of support | 15th December
| Ensure referee statements of support have been submitted to online portal | 19th December
| Finalise costs with PC and costing submitted to workflow | by 5th January
| Submit application for institutional approval minimum 48h before funder deadline. | 5th January

## RAEng ECR
RAEng Fellowships - Deadline 18th September 2024 | Timeline
Briefing session | 28th March
Candidate to identify supporting academic and notify scieng-submit@glasgow.ac.uk of intention to submit and supporting academic's name. | 16th April
Submit RAEng application template with statement from supporting academic to scieng-submit@glasgow.ac.uk | 2nd May
RAEng review panel meets to shortlist candidates | w/b 13th May
Interviews | w/b 27th May
Successful applicants notified | 3rd June
Complete costing request form and submit to CoSE-Researchoffice@glasgow.ac.uk. This will start the process of working with your PC. | 11th June
Initial costs to Project Coordinator | 18th June
Draft application to be submitted to your assigned RDM | 3rd July
Peer review session | will be arranged if appropriate for candidates/ fields
LKAS application submitted | 24th July
Draft letter of support to be sent to Research Development Manager and supporting academic for review/feedback - write it assuming LKAS has been approved. | 1st August
Finalise costs with PC and costing submitted to workflow | 4th September
Letter of support to be sent to HoS (In Engineering LoS must be approved first by Head of Research Division - allow an extra week ) | 2nd September
Submit application for institutional approval minimum of 48h before funder deadline. | 16th September

## Royal Society URF
Royal Society URF - Deadline 10th September | Timeline
Briefing session | 30th April
Candidate to identify supporting academic and notify scieng-submit@glasgow.ac.uk of intention to submit and supporting academic's name. | 15th May
Submit completed template to supporting academic | 28th May
Supporting academic reviews and submits to scieng-submit@glasgow.ac.uk with statement of support | 10th June
Approval to proceed with application and to apply for LKAS from panel | by 20th June
Complete costing request form and submit to CoSE-Researchoffice@glasgow.ac.uk. This will start the process of working with your PC. | 10th July
Call opens online: https://royalsociety.org/grants/university-research/ | 11th July
Final date to identify external candidates | 18th July
Draft application to be submitted to designated RDM | 1st August
LKAS application submitted | 6th August
Draft letter of support to be sent to Research Development Manager and supporting academic for review/feedback - write it assuming LKAS has been approved. | 8th August
Letter of support to be sent to HoS (In Engineering LoS must be reviewed and approved by Head of Research Division - allow an extra week ) | 21st August
Finalise costs with PC and costing submitted to workflow | 27th August
Submit application for institutional approval minimum of 48h before funder deadline. | 6th September

## STFC ERF
STFC Ernest Rutherford Fellowships - Deadline: Late September 2024 | Timeline
This is managed by the Schools of Physics and Astronomy and Geographical and Earth Science as they are eligible to submit applicants. | STFC state a date in August, before which, candidates cannot be confirmed.
Details will be issued by the schools and once candidates are selected the Research Development Team and Project Coordinators will be notified to provide the necessary support.
Candidates and supporting academics confirmed | 14th August
Complete costing request form and submit to CoSE-Researchoffice@glasgow.ac.uk. This will start the process of working with your PC. | 14th August
Data Management plan required - check support available https://www.gla.ac.uk/myglasgow/datamanagement/ | 14th August
Identify nominated reviewer who will provide a letter of support, they must not be from the host institution. | 21st August
Initial costs to Project Coordinator | 23rd August
LKAS application submitted | 23rd August
Draft application to be submitted to designated RDM | 3rd September
draft narrative CV to be submitted to designated RDM | 5th September
Finalise costs with PC and costing submitted to workflow | 10th September
Submit application for institutional approval minimum of 48h before funder deadline. | XXth September

## Quantum
Leverhulme ECR Fellowship - Deadline 22nd February 2024 | Timeline
Candidate and supporting academic to complete template | 23rd February
Template submitted to scieng-submit@glasgow.ac.uk | 23rd February
Templates reviewed by School Director of Research and approval sought | 5th March
Initial costs to Project Coordinator | 11th March
LKAS application submitted | 20th March
Draft application to be submitted to your Research Development Manager | 20th March
Draft host organisation support text (1000 words) to be submitting to Research Development Manager (template will be provided) | 22nd March
Finalise costs with PC and costing submitted to workflow | 4th April
Submit application for institutional approval minimum 48h before funder deadline. | Monday 8th April