## Slide 1: AY 24/25 Timetabling Project Unroomed Events and Change Requests MVLS

## Slide 2: AY24/25 Plan
Un-roomed Event Resolution
June
Change Request Process
July-onwards
CMIS closes
Friday 26th April
Central Rooming
May
First Week of May
All Disability data returned
Tuesday 18th June
Timetable published
CMIS re-opens for Local Teaching Space allocations
Un-roomed events identified with SMTT leading on large and critical un-roomed events
Local Timetabler resources leading solutions for smaller un-roomed events
Change Request process opens (specific CR reasons for Un-roomed Events)
Weekly College Sessions Engagements continue with focus on un-roomed events
W/c 15th July
Change Request process opens (All essential changes)
All course data, including new and additional to be extracted to MyCampus
Facility data extracted to MyCampus
Meetings schedule extracted to MyCampus
Monday 29th of July
Checkpoint on opening space for non-teaching events
Reg/Enrol & Start of Semester 1
August
Monday 5th August
Registration & Enrolment opens
Tuesday 6th August
Online booking open for Local Non-Teaching Space

## Slide 3: Un-roomed Events Resolution Calls
Large Events & Time Critical Events
(greater than 50 in size, events in the first 1 month of teaching)
A resolution call will be scheduled with the identified roles within each of the schools
The calls will be led by SMTT who will suggest potential solutions, we do not anticipate all the identified roles will be required to attend every call however we do expect decision makers to be available.
SMTT will update the event in real time if a suitable option has been agreed.
2. All Other Un-roomed Events
(less than size 50)
Led through the coordinating TT resource already identified. The Timetabling and Enrolment Coordinator/ L&T Assistants should review local space first to resolve.
Should a Timetabling and Enrolment Coordinator/ L&T Assistants need to change the event (e.g. time/day) to find a central room, they should:
  Liaise with the L&T Convener, Head of School or Head of Course to be aware of potential clashes and explore available options to resolve.
  Raise a “Central Room Request” to SMTT to room the event via the Change Request process
The CR will be updated when a room has been allocated
In the event there is no resolution that can be accommodated the Timetabling and Enrolment Coordinator/ L&T Assistants should escalate through the identified roles listed for Category 1 events.
Process
All un-roomed events identified by Tuesday, 18th June. SMTT will split the events into two categories

## Slide 4
Can Event be roomed ?
Event Updated by SMTT
College representatives to own ‘unresolved event’ offline before setting up call with SMTT
Escalated Call
End
Can Event be roomed ?
End
Final decision
Call organised with Deans of L&T, Student Ops Manager and if appropriate Frank and Moira.
Identified Roles (School Dependant)
Roles involved in these calls have been identified for each school.
Yes
No
Yes
No
Escalation Process Un-roomed Events
Un-roomed Event identified
Category ?
Category 1
Can local space resolve the event?
Event Roomed Locally (as per local process)
No, Central Space required
Yes
End
End
Category 2
SMTT to set up call with College representatives to resolve
L&T Admin to set up a call with College representatives
Can Event be roomed ?
Event updated by L&T Admin, submit request to SMTT for rooming
Yes
No
Senior L&T Admin escalates issue to the roles for resolution as per Escalation Point 1.
End
Un-roomed Events list provided to L&T Admin​
Note
Larger events will always take priority over smaller events. Therefore a move of a set of Lectures, may impact a series of smaller seminars.
Identified Roles (School Dependant)
Roles involved in these calls have been identified for each school.
Identified Roles (School Dependant)
Roles involved in these calls have been determined by the Advisory Group at a school level.
Please see slide 6 to 11 for details on the roles identified for each school.

## Slide 5
Escalation Process Medicine
Escalation Process | Critical Studies | Course
Name | Role | Course
Maureen Bain (UG) | Dean of L&T | All
Cheryl Woolhead (PGT) | Dean of PGT | All
Malcolm Shepherd (UMS) Helen Lloyd | Head of School UG Medical School Manager | All
Escalation Process:
If a resolution cannot be found for the event, this should be escalated within the School/College to the following roles (not all of these roles will need to be included, this will be dependent on the event and reason for un-resolution):
Resolution Calls:
Large Events & Time Critical Events (greater than 50 in size, events in the first 1 month of teaching) – calls will be organised by SMTT on a daily, ad-hoc basis. The events will be prioritised by size. SMTT will update the event in real time if a suitable option has been agreed. If a solution cannot be found, the School will escalate as per the agreed Escalation Process.
2. All Other Un-roomed Events (less than size 50) - led by the L&T Admin Assistant who will liaise with the Programme/Course Leads to be aware of potential clashes and explore available options to resolve. They will raise a “Central Room Request” to SMTT to room the event via the Change Request process. If a solution cannot be found, the School will escalate as per the agreed Escalation Process.
Resolution Call |  | Course
Name | Role | Course
Multiple (L&T Admin to identify) | Programme/Course Leads | All
Nicola Cumming Veronika Flaskarova Clair Hutcheson Eimear King Giedre Marozaite Claudia Rosillo | L&T Administrator | All
Veronika Flaskarova | Teaching Admin Officer Clinical | All
Nicola Cumming | Teaching Admin Officer Pre-Clinical | All
Resolution Call |  | Course
Name | Role | Course
Multiple (L&T Admin to identify) | Programme/Course Leads | All
Nicola Cumming Veronika Flaskarova Clair Hutcheson Eimear King Giedre Marozaite Claudia Rosillo | L&T Admin Administrator | All
Veronika Flaskarova | Teaching Admin Officer Clinical | All
Nicola Cumming | Teaching Admin Officer Pre-Clinical | All
L&T Admin Assistant responsible for assessing timetabling clashes.

## Slide 6
Escalation Process Nursing
Resolution Call |  | Course
Name | Role | Course
Multiple (L&T Admin to identify) | Programme/Course Leads | All
Renata Boschi Jillian Holland | L&T Admin Assistant | All
Escalation Process | Critical Studies | Course
Name | Role | Course
Maureen Bain (UG) | Dean of L&T | All
Cheryl Woolhead (PGT) | Dean of PGT | All
Eileen Cowey | Head of School | All
Escalation Process:
If a resolution cannot be found for the event, this should be escalated within the School/College to the following roles (not all of these roles will need to be included, this will be dependent on the event and reason for un-resolution):
Resolution Calls:
Large Events & Time Critical Events (greater than 50 in size, events in the first 1 month of teaching) – calls will be organised by SMTT on a daily, ad-hoc basis. The events will be prioritised by size. SMTT will update the event in real time if a suitable option has been agreed. If a solution cannot be found, the School will escalate as per the agreed Escalation Process.
2. All Other Un-roomed Events (less than size 50) - led by the L&T Admin Assistant who will liaise with the Programme/Course Leads to be aware of potential clashes and explore available options to resolve. They will raise a “Central Room Request” to SMTT to room the event via the Change Request process. If a solution cannot be found, the School will escalate as per the agreed Escalation Process.
Resolution Call |  | Course
Name | Role | Course
Multiple (L&T Admin to identify) | Programme/Course Leads | All
Renata Boschi Jillian Holland | L&T Admin Assistant | All
L&T Admin Assistant responsible for assessing timetabling clashes.

## Slide 7
Escalation Process Psychology & Neuroscience
Resolution Call |  | Course
Name | Role | Course
Multiple (L&T Admin to identify) | Programme/Course Leads | All
Lynda Young Donna Carrick | Learning & Teaching Manager Teaching Admin | All
Escalation Process | Critical Studies | Course
Name | Role | Course
Maureen Bain (UG) | Dean of L&T | All
Cheryl Woolhead (PGT) | Dean of PGT | All
Heather Cleland Woods | Director of Education | All
Escalation Process:
If a resolution cannot be found for the event, this should be escalated within the School/College to the following roles (not all of these roles will need to be included, this will be dependent on the event and reason for un-resolution):
Resolution Calls:
Large Events & Time Critical Events (greater than 50 in size, events in the first 1 month of teaching) – calls will be organised by SMTT on a daily, ad-hoc basis. The events will be prioritised by size. SMTT will update the event in real time if a suitable option has been agreed. If a solution cannot be found, the School will escalate as per the agreed Escalation Process.
2. All Other Un-roomed Events (less than size 50) - led by the L&T Admin Assistant who will liaise with the Programme/Course Leads to be aware of potential clashes and explore available options to resolve. They will raise a “Central Room Request” to SMTT to room the event via the Change Request process. If a solution cannot be found, the School will escalate as per the agreed Escalation Process.
Resolution Call |  | Course
Name | Role | Course
Multiple (L&T Admin to identify) | Programme/Course Leads | All
Lynda Young Donna Carrick | Learning & Teaching Manager Teaching Admin | All
Teaching Admin responsible for assessing timetabling clashes.

## Slide 8
Escalation Process Life Sciences
Resolution Call |  | Course
Name | Role | Course
Multiple (L&T Admin to identify) | Programme/Course Leads | All
Jack Scott Lynne Kelly (Additional Support Timetablers if needed) | L&T Admin Assistant/Lead Timetabler IT Manager/Support Lead Timetabler | All
Escalation Process | Critical Studies | Course
Name | Role | Course
Maureen Bain (UG) | Dean of L&T | All
Iain Johnstone Lillias Robinson Relevant Director of Education (Theresa Taylor to advise) | Assoc Dean LifeSci Portfolio HoPS Life science support unit | All
Multiple (IAJ/LR to advise) | Director of Education | All
Jack Scott | L&T Admin Assistant | All
Escalation Process:
If a resolution cannot be found for the event, this should be escalated within the School/College to the following roles (not all of these roles will need to be included, this will be dependent on the event and reason for un-resolution):
Resolution Calls:
Large Events & Time Critical Events (greater than 50 in size, events in the first 1 month of teaching) – calls will be organised by SMTT on a daily, ad-hoc basis. The events will be prioritised by size. SMTT will update the event in real time if a suitable option has been agreed. If a solution cannot be found, the School will escalate as per the agreed Escalation Process.
2. All Other Un-roomed Events (less than size 50) - led by the L&T Admin Assistant who will liaise with the Programme/Course/ Year Leads to be aware of potential clashes and explore available options to resolve. They will raise a “Central Room Request” to SMTT to room the event via the Change Request process. If a solution cannot be found, the School will escalate as per the agreed Escalation Process.
Resolution Call |  | Course
Name | Role | Course
Multiple (L&T Admin to identify) | Programme/Course Leads | All
Jack Scott | L&T Admin Assistant | All
L&T Admin Assistant responsible for assessing timetabling clashes.

## Slide 9
Escalation Process Post Graduate Studies
Resolution Call |  | Course
Name | Role | Course
Multiple (L&T Admin to identify) | Programme/Course Leads | All
Katherine Howes | Senior PGT Administrator | All
Escalation Process | Critical Studies | Course
Name | Role | Course
Cheryl Woolhead (PGT) | Dean of L&T | All
Laura Baggley (primary escalation contact) | PGT Manager | All
Katherine Howes | Senior PGT Administrator | All
Escalation Process:
If a resolution cannot be found for the event, this should be escalated within the School/College to the following roles (not all of these roles will need to be included, this will be dependent on the event and reason for un-resolution):
Resolution Calls:
Large Events & Time Critical Events (greater than 50 in size, events in the first 1 month of teaching) – calls will be organised by SMTT on a daily, ad-hoc basis. The events will be prioritised by size. SMTT will update the event in real time if a suitable option has been agreed. If a solution cannot be found, the School will escalate as per the agreed Escalation Process.
2. All Other Un-roomed Events (less than size 50) - led by the L&T Admin Assistant who will liaise with the Programme/Course Leads to be aware of potential clashes and explore available options to resolve. They will raise a “Central Room Request” to SMTT to room the event via the Change Request process. If a solution cannot be found, the School will escalate as per the agreed Escalation Process.
Resolution Call |  | Course
Name | Role | Course
Multiple (L&T Admin to identify) | Programme/Course Leads | All
Katherine Howes | Senior PGT Administrator | All
Senior PGT Administrator responsible for assessing timetabling clashes.

## Slide 10
Escalation Process Vet Medicine – When Required
Resolution Call |  | Course
Name | Role | Course
Multiple (L&T Admin to identify) | Programme/Course Leads | All
Lumba Chirwa | L&T Admin Assistant | All
Escalation Process | Critical Studies | Course
Name | Role | Course
Maureen Bain (UG) | Dean of L&T | All
Cheryl Woolhead (PGT) | Dean of PGT | All
Neil Evans | Director of Education | All
Arlene Macrae | Undergraduate School Manager | All
Escalation Process:
If a resolution cannot be found for the event, this should be escalated within the School/College to the following roles (not all of these roles will need to be included, this will be dependent on the event and reason for un-resolution):
Resolution Calls:
Large Events & Time Critical Events (greater than 50 in size, events in the first 1 month of teaching) – calls will be organised by SMTT on a daily, ad-hoc basis. The events will be prioritised by size. SMTT will update the event in real time if a suitable option has been agreed. If a solution cannot be found, the School will escalate as per the agreed Escalation Process.
2. All Other Un-roomed Events (less than size 50) - led by the L&T Admin Assistant who will liaise with the Programme/Course Leads to be aware of potential clashes and explore available options to resolve. They will raise a “Central Room Request” to SMTT to room the event via the Change Request process. If a solution cannot be found, the School will escalate as per the agreed Escalation Process.
Resolution Call |  | Course
Name | Role | Course
Multiple (L&T Admin to identify) | Programme/Course Leads | All
Lumba Chirwa | L&T Admin Assistant | All
L&T Admin Assistant responsible for assessing timetabling clashes.

## Slide 11
Escalation Process Dentistry – When Required
Resolution Call |  | Course
Name | Role | Course
Same as above table | Programme/Course Leads | All
Same as above table | L&T Admin Assistant | All
Escalation Process | Critical Studies | Course
Name | Role | Course
Maureen Bain (UG) | Dean of L&T | All
Cheryl Woolhead (PGT) | Dean of PGT | All
Aileen Bell/ Andrew Forgie | Head of School Director of Education | All
Escalation Process:
If a resolution cannot be found for the event, this should be escalated within the School/College to the following roles (not all of these roles will need to be included, this will be dependent on the event and reason for un-resolution):
Resolution Calls:
Large Events & Time Critical Events (greater than 50 in size, events in the first 1 month of teaching) – calls will be organised by SMTT on a daily, ad-hoc basis. The events will be prioritised by size. SMTT will update the event in real time if a suitable option has been agreed. If a solution cannot be found, the School will escalate as per the agreed Escalation Process.
All Other Un-roomed Events (less than size 50) - led by the L&T Admin Assistant who will liaise with the Programme/Course/ Year Leads to be aware of potential clashes and explore available options to resolve. They will raise a “Central Room Request” to SMTT to room the event via the Change Request process. If a solution cannot be found, the School will escalate as per the agreed Escalation Process.
Resolution Call |  | Course
BDS 1 Neil Nairn BDS 2 Robert McKerlie BDS 3 Craig Mather BDS 4 Kurt Naudi BDS 5 (James) Alun Scott | Programme/Course Leads | See code against name= Bachelor of Dentistry YEAR
BDS 1 Susan Lumgair BDS 2 Jessica Brewster BDS 3 Ashley McMillan BDS 4 Susan Johnston BDS 5 Claire Rodgers | L&T Admin Assistant | See code against name= Bachelor of Dentistry YEAR
L&T Admin Assistant responsible for assessing timetabling clashes.

## Slide 12
No. | Essential Reason | Description
5 | Accessibility requirement | If an accessibility requirement was not identified during Edit & Prep or if the requirement has changed. Include information on the nature of the accessibility that needs to be accommodated, e.g. wheelchair access, hearing assistance, etc.
6 | Change in size | If the number of students enrolled differs from the allocated space and the room is no longer suitable. Update the size of associated subgroup(s) before submitting a change request.
No. | Essential Reason | Description
1 | Room no longer required | If a room is no longer required due to an event being cancelled, changed to online, or roomed locally
2 | Central room request | For existing un-roomed events that you have found a solution for.
3 | Use of another area's local space | If you have agreed to use another School’s local space. Include the evidence of the agreement with the local space manager in the Supporting Documents field
4 | Data quality issue | To rectify data entry issues in CMIS, for example updating the contact, swapping like-for-like courses or subgroups on events, changing the Source on events, etc.
Clear description of change required in “Change Description” section of Change Request Form
7 | New course/event | New courses approved after the end of Edit & Prep or new events on existing courses. The timing of events should be checked against availability of spaces before submitting a request.
8 | Time/Day change | If the date, time, or duration of an existing event needs to be changed. The timing of events should be checked against availability of spaces before submitting a request.
9 | Equipment/Features change | If the room allocated does not have the required equipment and/or features, Include details of the requirement. For accessibility requirements use the separate reason for this purpose.
10 | 'Opt-out' of lecture recording (as per policy) | If the event has been tagged for lecture recording, but the academic wants to opt-out of recording. Where possible please ensure the lecturer’s name is attached to the event in CMIS.
Essential Change Requests
Reasons for AY 24-25
Un-roomed events period
Change request period – additional reasons
No approval required for submitting a Change Request
New

## Slide 13: Escalation Process Change Requests
Event Updated by SMTT
End
Reject CR
End
Yes
No
Yes
No
Change Request submitted to SMTT
Sufficient/ accurate detail added for the type of CR?
Can we accommodate ?
Change Required ?
End
No
Escalate via Un-roomed Process (Class size less than 50)
End
Yes

## Slide 14: Un-roomed Events & Change Requests Project Communications Campaign – to be updated
Un-roomed Event Process
June
Change Request Process
July-onwards
April
Central Rooming
May
28th May
SMG
Monday 3rd June
CMG one-pager
Monday 1st July
CMG and SMG
Forums
26th April
CMIS closes (CMIS users + HoPS)
Comms
18th June
Timetable released
email
w/c 15th July
Change Requests opens
Bi –weekly College Engagement Sessions
Reporting
w/c 24th June >
Weekly Un-roomed Progress Reporting
w/c 15th July >
Weekly Change Request Reporting
w/c 3rd June
Project update and video message from Project Sponsors (+ specific role comms for Un-roomed Events and Change Requests)